New Agent Training Plan

Adjust the length to the complexity of your program: a simple inbound queue may need 2 weeks of classroom training, a regulated financial or healthcare queue 5 to 8. Each week ends with a gate the trainee must pass before moving on. Record results on the class tracker daily.

CLASS DETAILS

Program / line of business:

Class ID / cohort name:

Site or virtual:   ☐ On site     ☐ Virtual     ☐ Hybrid

Lead trainer:

Nesting supervisor / team lead:

Class start date:

Planned floor (production) date:

Number of trainees at start:

Training hours per day:

PRE-START (BEFORE DAY 1)

☐  System access requested for every trainee: network login, CRM, telephony/softphone, knowledge base, LMS, timekeeping

☐  Equipment shipped and confirmed for remote trainees (headset, computer, any security tokens)

☐  Welcome message with schedule, dress code or camera expectations, parking or login instructions and the trainer's contact details

☐  New hire paperwork and required compliance acknowledgements completed

☐  Training room, virtual classroom and training environment (sandbox accounts) tested

☐  Nesting team lead and floor buddies assigned

WEEK 1: COMPANY, CUSTOMER AND CORE SYSTEMS

☐  Day 1: Welcome, introductions, the program and its customers, policies, attendance rules, how pay and schedules work

☐  Day 1-2: Security, privacy and compliance training (data protection, PCI if handling cards, call recording notice, HIPAA or other program rules)

☐  Day 2-3: Systems walkthrough in the training environment: CRM, telephony states, disposition codes, ticketing, knowledge base search

☐  Day 3-4: Top 5 call types by volume: what the customer wants, the steps to resolve, the policies behind them

☐  Day 4-5: Call flow and script walkthrough, verification process, hold and transfer procedure

☐  Daily: 30 minutes listening to recorded calls with a guided worksheet

☐  Gate 1: Policy and systems quiz, pass mark [80]%; navigation test completing [5] common tasks in the training environment

WEEK 2: CALL HANDLING SKILLS AND REMAINING CALL TYPES

☐  Next 5 to 10 call types by volume, plus how to recognize calls that must be escalated

☐  Soft skills: listening, specific acknowledgement, plain language, managing silence and hold time

☐  De-escalation and handling difficult or abusive callers

☐  Notes and documentation standards, with graded note-writing exercises

☐  Daily roleplays in pairs, rising in difficulty, with trainer feedback against the QA form

☐  Introduction to the QA scorecard and how agents are measured (QA, CSAT, FCR, AHT, adherence)

☐  Gate 2: Graded roleplays on [4] call types scoring [80]% or higher on the QA form; product and process knowledge test pass mark [80]%

WEEK 3: SUPERVISED LIVE CALLS (TRAINING BAY)

☐  Side-by-side: trainee listens live to an experienced agent for [4] hours, then takes calls while the agent listens

☐  Trainee takes live calls on a limited queue (simplest call types only) with trainer or floor support at hand

☐  Daily huddle: review of the hardest calls of the previous day

☐  [2] scored QA evaluations per trainee per day, reviewed the same day

☐  Remaining call types and edge cases introduced as trainees handle real volume

☐  Gate 3: Average QA of [80]% across the week, zero compliance auto-fails, trainer sign-off on readiness for nesting

WEEK 4 ONWARD: NESTING

☐  Class moves to a dedicated nesting team with a higher support ratio (one team lead or floor coach per [8 to 12] agents)

☐  Full queue with adjusted targets: AHT target [130-150]% of production in week 1 of nesting, stepping down weekly

☐  Daily QA evaluation and short coaching for each agent

☐  Daily nesting metrics review: QA, AHT, hold time, transfers, adherence

☐  Graduation criteria to production: QA at or above [85]% for [5] consecutive days, AHT within [115]% of target, no compliance misses, adherence at or above [90]%

☐  Agents who miss graduation criteria get a defined extension (up to [1] week) with a written plan

CLASS RESULTS AND SIGN-OFF

Trainees at start:

Trainees who passed each gate (Gate 1 / 2 / 3):

Trainees who graduated to production:

Training attrition % ((start - graduated) / start x 100):

Average days to reach production targets:

Main reasons trainees left or failed:

Changes recommended for the next class:

Trainer signature:                                                            Date:

Operations manager signature:                                                            Date:

Date: